## TSR, TSO and Tasks
S/No | Item | Expected Date | Status | Remarks
1 | Framework and other Logical units like Entities and DTO | 2017-10-03 | Done
2 | Web APIs and Services | Ongoing | Done | News methods are added as per the requirements
3 | Login Page | 2017-10-04 | Done
4 | Masters: Vertical Page, DTO, Entities and Service | 2017-10-05 | Done
5 | Masters: Practice Page, DTO, Entities and Service | 2017-10-05 | Done
6 | Masters: Solution Centre Page, DTO, Entities and Service | 2017-10-05 | Done
7 | Masters: Client Region Page, DTO, Entities and Service | 2017-10-09 | Done
8 | Masters: Market Offering Page, DTO, Entities and Service | 2017-10-09 | Done
9 | Masters: Operational Risk Page, DTO, Entities and Service | 2017-10-09 | Done
10 | Masters: Core Services Page, DTO, Entities and Service | 2017-10-10 | Done
11 | Masters: Relevent Repositories Page, DTO, Entities and Service | 2017-10-10 | Done
12 | Masters: Service Delivery Chain Page, DTO, Entities and Service | 2017-10-10 | Done
13 | Masters: User Mantenance Page, DTO, Entities and Service | 2017-10-12 | Done | User Activation and Locking features
14 | Masters: User TSR assignment page, DTO, Entities and Service |  |  | If required, this feature will enable only nominated users to view TSR*
15 | Masters: User TSO assignment page, DTO, Entities and Service |  |  | If required, this feature will enable only nominated users to view TSO*
16 | Site: Create TSR Page, DTO, Entities and Service | 2017-10-18 | Done
17 | Site: Create TSO Page, DTO, Entities and Service | 2017-10-24 | Done
18 | Site Dashboard | 2017-10-27 | Done

## Tasks CRs
S/No | Item | Expected Date | Status | Remarks
1 | New fields addition to Task Entites, DTO | 2018-01-11 | In-Progress
2 | New fields addition to Task table in DB | 2018-01-11 | In-Progress
3 | New fields addition on the web page | 2018-01-12
4
5
6
7

## Changes discussed on 12-01-2018
S/No | Item | Expected Date | Status | Remarks
1 | TSR: All fields mandatory | 2018-01-16 | Done
2 | TSR: Yellow top comments removal | 2018-01-16 | Done
3 | TSR: Remove 'Delete' button | 2018-01-16 | Done
4 | TSR: Remove Created By and Updated By columns, replace it with 'Modified By' | 2018-01-16 | Done
5 | TSR: Add ERP order description field | 2018-01-16 | Done
6 | TSR: Engagement Dropdown | 2018-01-17 | Done
7 | Masters: Engagement, DTO, Entities and Service | 2018-01-17 | Done
8 | Masters: Client, DTO, Entities and Service | 2018-01-18 | Done
9 | TSR: Add TSR Status in the Edit Mode | 2018-01-18 | Done
10 | TSR: TSR Status to displayed on Dashboad heading in place of created by | 2018-01-18 | Done
11 | TSR: Assignment mail to sent to all the selected managers | 2018-01-19 | Done
12 | TSR: Dashboard: Collapsable panel to view all the fields in the view mode | 2018-01-19 | Done
13 | TSO: All fields mandatory | 2018-01-22 | Done
14 | TSO: Yellow top comments removal | 2018-01-22 | Done
15 | TSO: Remove QG Passed | 2018-01-22 | Done
16 | TSO: Add TSO Status in the Edit Mode | 2018-01-22 | Done
17 | TSO: Dashboard - Add TSO status column | 2018-01-23 | Done
18 | TSO: Dashboard: Add Effort Calculation column | 2018-01-23 | Done
19 | TRO: Dashboard: Collapsable panel to view all the fields in the view mode | 2018-01-24 | Done
20 | Tasks: All fields mandatory | 2018-01-25 | Done
21 | Tasks: Replace 'Person days' to 'Working days' in processing time field | 2018-01-29 | Done
22 | Tasks: Remove 'Person days' from Service Quality field | 2018-01-29 | Done
23 | Tasks: New Group for Productivity fields | 2018-01-29 | Done
24 | Tasks: New Group for Defect fields | 2018-01-30 | Done
25 | Tasks: New Group for Service Quality | 2018-01-30 | Done
26 | Tasks: Add/Edit header to replaced with Tasks | 2018-01-30 | Done
27 | Tasks: Add planned fields to be disabled in the 'Edit' mode (after first entry) | 2018-01-30 | Done
28 | Role Based access | 2018-02-02